## Timeline
Task/Phase | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8
Requirements | bar: Week 1
Design | bar: Week 2 to Week 3
Development | bar: Week 3 to Week 5
Testing & QA | bar: Week 6
Launch & Training | bar: Week 7 to Week 8

## Gantt Chart
Task/Phase | Start Week | Duration
Requirements | 1 | 1
Design | 2 | 2
Development | 3 | 3
Testing & QA | 6 | 1
Launch & Training | 7 | 2